## DATA
PROJECT PIPELINE TRACKER |  |  |  |  | Visit indzara.com
[5 empty] | Password to unprotect: indzara |  |  |  |  | COMPLETED PROJECTS
| ENTER UP TO 6 STAGES |  |  |  | Please do not rename the STAGE DT fields
STAGE NAME
RESEARCH
APPROVAL
| DEVELOP | ACTIVE PIPELINE | [7 empty] | AVG. DURATION (DAYS)
TEST
EXECUTE
LAUNCH
ENTER PROJECTS |  |  | RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH |  |  | Calculated | Calculated | Calculated | Calculated
PROJECT ID | NAME | START DATE | STAGE 1 DT | STAGE 2 DT | STAGE 3 DT | STAGE 4 DT | STAGE 5 DT | STAGE 6 DT | TYPE | OWNER | CURRENT STAGE | COMPLETION DATE | DURATION (DAYS) | VALIDATION
1 | Project One | 2016-05-01 | 2016-05-06 | 2016-05-06 | 2016-05-15 |  |  |  | Internal | Project Manager 1 | TEST |  | 100 | NO ERROR
2 | Project Two | 2016-05-05 | 2016-05-12 | 2016-05-13 | 2016-05-15 | 2016-05-18 | 2016-05-20 | 2016-05-21 | External | Project Manager 2 | COMPLETED | 2016-05-21 | 17 | NO ERROR
3 | Project Three | 2016-06-02 | 2016-06-07 | [5 empty] | Internal | Project Manager 1 | APPROVAL |  | 68 | NO ERROR
4 | Project four | 2016-06-01 | 2016-06-05 | [5 empty] | External | Project Manager 1 | APPROVAL |  | 69 | NO ERROR
5 | Project Five | 2016-06-02 |  | 2016-06-05 |  |  |  |  | Internal | Project Manager 2 | DEVELOP |  |  | ERROR
6 | Project Six | 2016-06-03 | 2016-06-04 | 2016-06-06 |  |  |  |  | External | Project Manager 1 | DEVELOP |  | 67 | NO ERROR
7 | Project Seven | 2016-06-04 | 2016-06-05 | 2016-06-07 | 2016-06-08 |  |  |  | Internal | Project Manager 1 | TEST |  | 66 | NO ERROR
8 | Project Eight | 2016-06-05 | 2016-06-08 | 2016-06-09 | 2016-06-11 | 2016-06-13 | 2016-06-15 |  | External | Project Manager 1 | LAUNCH |  | 65 | NO ERROR
9 | Project Nine | 2016-06-05 | 2016-06-08 | 2016-06-09 | 2016-06-11 | 2016-06-13 | 2016-06-13 | 2016-06-13 | External | Project Manager 1 | COMPLETED | 2016-06-13 | 9 | NO ERROR
10 | Project Ten | 2016-06-06 | 2016-06-08 | 2016-06-09 | [5 empty] | Project Manager 2 | DEVELOP |  | 64 | NO ERROR
11 | Project Eleven | 2016-05-01 | [7 empty] | Project Manager 3 | RESEARCH |  | 100 | NO ERROR
12 | Project Twelve | 2016-04-01 | 2016-04-02 | 2016-04-03 | 2016-04-10 | 2016-04-20 | 2016-04-25 | 2016-04-28 | External | Project Manager 2 | COMPLETED | 2016-04-28 | 28 | NO ERROR
13 | Project Thirteen | 2016-03-01 | 2016-03-02 | 2016-03-08 | 2016-03-09 | 2016-03-12 | 2016-03-14 | 2016-03-20 | Intenal | Project Manager 1 | COMPLETED | 2016-03-20 | 20 | NO ERROR
14 | Project Fourteen | 2016-03-01 | 2016-03-02 | 2016-03-08 | 2016-03-09 | 2016-03-12 | 2016-03-14 | 2016-03-20 | Intenal | Project Manager 1 | COMPLETED | 2016-03-20 | 20 | NO ERROR
15 | Project Fifteen | 2016-06-02 | 2016-06-05 | 2016-06-08 | [6 empty] | DEVELOP |  | 68 | NO ERROR
Formulas:
COMPLETION DATE = IF(T_PROJ[[#This Row],[CURRENT STAGE]]="COMPLETED",INDEX(T_PROJ[],ROW(T_PROJ[[#This Row],[PROJECT ID]])-ROW(T_PROJ[[#Headers],[PROJECT ID]]),MATCH("STAGE "&N_ST&" DT",T_PROJ[#Headers],0)),"")
1
2
3
2
0
9
1
5
19

## ACTIVE PIPELINE
RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH
Project Eleven | Project Three | Project Six | Project One |  | Project Eight
11 | 3 | 6 | 1 |  | 8
| Internal | External | Internal |  | External
Project Manager 3 | Project Manager 1 | Project Manager 1 | Project Manager 1 |  | Project Manager 1
| Project four | Project Ten | Project Seven
| 4 | 10 | 7
| External |  | Internal
| Project Manager 1 | Project Manager 2 | Project Manager 1
Project Fifteen
15
2
1
3
2
0
1

## REPORT
MONTHLY REPORT
Avg Duration in each Stage
|  | Projects Completed | Avg. Duration | RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH
| 2016-08-01 | 0
| 2016-07-01 | 0
| 2016-06-01 | 1 | 9 | 4 | 1 | 2 | 2 | 0 | 0
| 2016-05-01 | 1 | 17 | 8 | 1 | 2 | 3 | 2 | 1
| 2016-04-01 | 1 | 28 | 2 | 1 | 7 | 10 | 5 | 3
| 2016-03-01 | 2 | 20 | 2 | 6 | 1 | 3 | 2 | 6

## H (hidden)
STAGES
6 |  | Columns and Rows are designed to match the Active Pipeline sheet. Any insert or delete columns/rows will mess the formulas.
OPEN PROJECTS | 9
|  | MANUAL ENTRY | RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH
STAGE | OPEN PROJECTS | 1 | 24 | 16 | 19 | 14 |  | 21
1 | 1 | 1 | 24 | 16 | 19 | 14 |  | 21
2 | 2 | 1 | 24 | 16 | 19 | 14 |  | 21
3 | 3 | 1 | 24 | 16 | 19 | 14 |  | 21
4 | 2
5 | 0 | 2 |  | 17 | 23 | 20
6 | 1 | 2 |  | 17 | 23 | 20
|  | 2 |  | 17 | 23 | 20
|  | 2 |  | 17 | 23 | 20
|  | 3 |  |  | 28
| AVG DURATION | 3 |  |  | 28
RESEARCH | 3.6 | 3 |  |  | 28
APPROVAL | 3 | 3 |  |  | 28
DEVELOP | 2.6
TEST | 4.2 | 4
EXECUTE | 2.2 | 4
LAUNCH | 3.2 | 4
4
COMPLETED PROJECTS
5 |  | 5
5
TODAY |  | 5
2016-08-08 |  | 5
MIN PROJ START DATE
2016-03-01
AVG DURATIOn | 18.8