## Slide 1
Expedite Project Updates Using a Custom Status View
June 20, 2018 @ 12pm-1pm EST
Presented By:
Walter M. Stinnett, Jr., PMP, CSM, MCTS
800.556.2506 | www.EdwPS.com
Notes: Start Recording
We are going to go ahead and get started with todays session on xxxxx.

## Slide 2: Objectives
Describe the importance of monitoring and controlling projects
Discuss why communication is key to successful projects
Define the schedule control process and the importance of accurate status
Create a custom status view to expedite project updates

## Slide 3: Five Project Management Processes
Initiating
Planning
Executing
Monitoring and Controlling
Closing
Graphic adapted from Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) –Sixth Edition, Project Management Institute Inc., 2017, Page 23

## Slide 4: Monitoring and Controlling Process
Track, review, and regulate project progress and performance
Identify any required plan changes
Initiate corresponding changes
Definitions from the Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017

## Slide 5: Project Schedule Management Knowledge Area
Processes required to ensure timely project completion
  Plan Schedule Management
  Define Activities
  Sequence Activities
  Estimate Activity Durations
  Develop Schedule
  Control Schedule
(6)
Project Schedule
Management
(9)
Project Resource
Management
(5)
(7)
(8)
(4)
(10)
(11)
(12)
(13)
Project Management Institute, A Guide to the Project Management Body of Knowledge, (PMBOK® Guide) – Sixth Edition, Project Management Institute Inc., 2017, Pages 24-25

## Slide 6: Why Use a Schedule Tool?
Why develop a detailed project work schedule?
  Communication (between you and your stakeholder/customer/client)
  Communication (between you and your project team)
  Communication (between you and your senior management)
Why use a scheduling tool like Microsoft Project?
  Calculate and display project task dates
  Calculate and display use of resources
  Assist in managing the schedule once developed
    Scheduling tools do NOT build a schedule
  Calculate the project critical path
  Track and communicate progress
  Set up and examine “What if” scenarios

## Slide 7: Control the Schedule
Controlling (or status updating) the project schedule involves
  Determining schedule changes
  Managing the actual changes, as they occur
To determine and manage project schedule changes, you must track the actual project progress against the original project plan (schedule baseline)

## Slide 8: Information Needed to Track Progress
Availability for each resource
  Was the resource available, as planned, during the status period?
  Is the resource going to be available, as planned, moving forward (to your knowledge)?
Task schedule for each task
  If the task started, when did task work begin (Actual Start)?
  If the task is complete, when did it finish (Actual Finish)?
  If the task is not complete
    How much calendar time (typically days or hours) has been spent on the task?
    How much more calendar time is needed?
Task cost for each resource, on each task
  How much work was expended on the task by the resource?
  How much work is needed, by each resource, to complete the work?

## Slide 9: Create a Custom Status View
Combines a task detail form with a task usage view, allowing updates in one view
  Actual start and finish
  Actual and remaining work
  Duration
  Percentage complete
  Resource assignments

## Slide 10: Custom Status View

## Slide 11: Our Project

## Slide 12: Create Base Custom Table
Step 1: Select the View tab
Step 2: Select More Tables from the Tables dropdown
Step 1: Select the View tab
Step 2: Select More Tables from the Tables dropdown

## Slide 13: Create Base Custom Table
Step 3: Select the Task radio button for table type
Step 4: Select the default Usage table from the list and click Copy
Step 3: Select the Task radio button for table type
Step 4: Select the default Usage table from the list and click Copy

## Slide 14: Create Base Custom Table
Step 5: Rename the table
Step 6: Modify the fields and adjust the formatting, if needed
Step 7: Click OK and to close Table Definition dialog
Step 8: Click Cancel to close More Tables dialog
Step 5: Rename the table
Step 6: Modify the fields and adjust the formatting, if needed
Step 7: Click OK and to close Table Definition dialog
Step 8: Click Cancel to close More Tables dialog

## Slide 15: Create Primary Custom View
Step 9: Select the View tab
Step 10: Select More Views from the Other Views dropdown from the Task Views group
Step 9: Select the View tab
Step 10: Select More Views from the Other Views dropdown from the Task Views group

## Slide 16: Create Primary Custom View
Step 11: Select the New button in the More Views dialog
Step 12: Select the Single view radio button in Define New View
Step 13: Select the following in the View Definition dialog
  Name: Enter name of new view
  Screen: Task Usage
  Table: Select the new custom table
  Group: No Group
  Filter: All Tasks
Step 11
Step 12
Step 13

## Slide 17: Create the Custom Status View
Step 14: Select the View tab
Step 15: Select More Views from the Other Views dropdown from the Task Views group
Step 14: Select the View tab
Step 15: Select More Views from the Other Views dropdown from the Task Views group

## Slide 18: Create Primary Custom View
Step 16: Select the New button in the More Views dialog
Step 17: Select the Combination view radio button in the Define New View dialog
Step 18: Select or enter the following in the View Definition dialog
  Name: Enter name of new view
  Primary View: Select the just created single view
  Details Pane: Task Details Form
Step 16
Step 18
Step 17

## Slide 19: Display Custom Status View
Step 19: Select the Task tab
Step 20: Select Combined Status Tracking from the Gantt Chart dropdown from the Task Views group
Step 19: Select the Tab tab
Step 20: Select Combined Status Tracking from the Gantt Chart dropdown from the Task Views group

## Slide 20: Custom Status View
Step 9: Select the View tab
Step 10: Select More Views from the Other Views dropdown from the Task Views group

## Slide 21: Modify Format of Task Usage Panel
Step 1: Right click anywhere in the task usage panel and select Detail Styles
Step 1: Right click anywhere in the task usage panel and select Detail Styles

## Slide 22: Add Fields to Task Usage View
Step 2: Select All Assignment Rows in the Show these fields list and click Hide to remove it from the view
Step 3: Select Baseline Work and Actual Work in the Available fields list and click Show to add them to the view
Step 3: Select Baseline Work and Actual Work in the Available fields list and click Show to add them to the view
Step 2: Select All Assignment Rows in the Show these fields list and click Hide to remove it from the view

## Slide 23: Modify Field Order and Cell Background Color
Step 4: Select Baseline Work in the Show these fields list and click the up Move arrow to move it to the top of the list
Step 5: Select Baseline Work, Work, and Actual Work fields in order and assign each a different cell color
Step 4: Select Baseline Work in the Show these fields list and click the up Move arrow to move it to the top of the list
Step 5: Select Baseline Work, Work, and Actual Work fields in order and assign each a different cell color

## Slide 24: Change the Font Style of Fields
Step 6: Select fields in order and click the Change Font button to modify font and/or font style
Step 6: Select fields in order and click the Change Font button to modify font and/or font style

## Slide 25: Completed Custom Status View
Save file as a .mpt project template or copy into other project schedules via the Organizer

## Slide 26
Questions?

## Slide 27
Thank You!
Presented By:
Walter M. Stinnett, Jr., PMP, CSM, MCTS
WStinnett@EdwPS.com
800.556.2506 | www.EdwPS.com
Notes: Start Recording
We are going to go ahead and get started with todays session on xxxxx.