## Slide 1
Data Analysis using Project with Excel
November 28, 2018 @ 12pm-1pm EST Jeff Bongiovani
Notes: Start Recording
We are going to go ahead and get started with todays session on xxxxx.

## Slide 2: Topic Outline
General Information
Database and Analysis Concepts
Adapting Microsoft Project
Microsoft Excel Analysis

## Slide 3: Intentions
Understand how to manage data in Microsoft Project intended for an ongoing data collection in Microsoft Excel
Understand how View, Tables, and Fields in Microsoft Project can be customized to enable this process
Understand how to maintain an ongoing data collection in Excel for the purposes of analysis

## Slide 4: Disclaimer
Requires a relatively advanced understanding of Project features
Only an overview of
  Project Views, Tables, and Custom Fields
  Excel Tables, Functions, and PivotTables
You may not find use in the overall process and example, but there may be tips and techniques that may help

## Slide 5: Background Information
IT Instructor for 12 years
Employed with State of Maryland for 2 years
IT Instructor again for 3 years
Instructional Designer for 7 months

## Slide 6: Database Concepts

## Slide 7: The Relational Database
Typically represents a central transaction or activity that involves relevant people, places, objects, and classifications
Each grouping of people, places, objects, classifications, and activities is stored within separate tables
  Each table contains a primary key unique identifier
  Each table contains relevant attributes for those entities uniquely identified
Unique information is stored only one time
Tables reference the unique identifiers of other tables with which they are associated
Customers
Orders
Order Line Items
Products

## Slide 8: Table Relationships
Parent to Child or One to Many
  Several customers may place orders over time
  A single customer could return multiple times
  Only one customer name appears on the order
  Every time that same customer places an order, we refer to that customer by the same identifier
Customers
Orders
Order Line Items
Products
1001 - A
1002 - B
1003 - A
A – Mike
B – Judy
C – Pat

## Slide 9: Join or Junction Relationships
Many for Many
  For each order, multiple products are purchased
  A single product could be sold multiple times
    By its title (i.e. not one specific jar of jam, but a name referring to the brand, type, and size of jam)
  The Order Number cannot be repeated in its table; the Product ID cannot be repeated in its table
Customers
Orders
Order Line Items
Products
1001 - A
1002 - B
1003 - A
Wine
Cheese
Pickles
1001 - Wine
1001 - Cheese
1002 - Cheese
1002 - Pickles
1003 - Wine

## Slide 10: Potential Analysis
Customers is connected to Orders
  Count the number of times a customer placed orders
  Count the number of customers within each month and show full name
Orders is connected to Order Line Items
  Sum each order total
Customers, by means of Orders, is connected to Order Line Items
  Analyze customer purchasing preferences
    How often, what to they buy, how much to they buy at a time?
Orders
Order Line Items
Products
1001 - A
1002 - B
1003 - A
Wine
Cheese
Pickles
1001 - Wine
1001 - Cheese
1002 - Cheese
1002 - Pickles
1003 - Wine
Customers
A – Mike
B – Judy
C – Pat

## Slide 11: Grouping and Aggregate Formulas
Orders
Order Line Items
Products
1001 - A
1002 - B
1003 - A
Wine
Cheese
Pickles
1001 - Wine
1001 - Cheese
1002 - Cheese
1002 - Pickles
1003 - Wine
Customers
A – Mike
B – Judy
C – Pat
Orders
Order | Customer | Date
1001 | A | 1/1/2019
1002 | B | 1/6/2019
1003 | A | 1/11/2019
1004 | C | 1/16/2019
1005 | A | 1/21/2019
1006 | D | 1/26/2019
1007 | F | 1/31/2019
1008 | E | 2/5/2019
1009 | A | 2/10/2019
1010 | C | 2/15/2019
1011 | A | 2/20/2019
Customers | Jan 2019 | Feb 2019 | Total
Mike | 3 | 2 | 5
Judy | 1 |  | 1
Pat | 1 | 1 | 2
Jimmy | 1 |  | 1
Heather |  | 1 | 1
Francine | 1 |  | 1
Total | 7 | 4 | 11

## Slide 12: Each Project is a Database
Multiple tasks need to be performed
Multiple resources may be needed to perform those tasks
For each individual task, multiple resources may be assigned
Each resource may be assigned to multiple tasks
Tasks
Assignments
Resources

## Slide 13: Project Views
Task Views
  Gantt Chart
  Task Sheet
Resource Views
  Resource Sheet
Assignment Views
  Task Usage
  Resource Usage
Tasks
Assignments
Resources

## Slide 14: Anatomy of Project Views
Single or Combination
Screen
  Data Focus (i.e. Tasks, Resources, Assignments)
  Chart, Detail Grid, or other Visual Display
Data Table (initial default)
Text Styles and Bar Styles
Other
  Print Setup
  Filter and Highlight
  Timescale

## Slide 15: The Project Table Concept
Queries or SQL Views
A collection of data columns represented by a useful name
% Complete
% Work Complete
Actual Cost
Actual Duration
Actual Work
Baseline Cost
Baseline Duration
Baseline Work
Cost
Duration
Finish Date
Name
Remaining Work
Start Date
Work
…20,000+ data fields
EXISTING PROJECT TASK COLUMNS
THE ENTRY TABLE WHEN I’M USING THE GANTT CHART
Indicators
Task Type
Name
Duration
Start Date
Finish Date
Predecessors
Resources

## Slide 16: Existing Project Tables
Data will be relative to the current view
For example, if you open the Task Usage View and show the Cost Table, you will see current, baseline, actual cost data for assignments.
 | Current Expectation (Planned and Real) | Original Expectation (Baseline) | Actuals Comparisons
Durations Dates | Entry, Usage | Baseline | Tracking
Work | Usage, Work | Work, Baseline | Work, Tracking
Cost | Cost | Cost, Baseline | Cost, Tracking

## Slide 17: Project Custom Fields
Text Columns
Number Columns and Calculations
Number1 (Total Cases)
Number2 (Remaining Cases)
Number3 (Cases Processed)
Number4 (Cases Per Hour Est)
Number5 (Estimated Hours)
Text1 (Branch Office)
Text2 (Project Name)
Text3 (Case Type)
Text4
Text5
Text6
Text7
Text8
…20,000+ data fields
CUSTOMIZABLE PROJECT TASK COLUMNS
THE CUSTOMIZED ENTRY TABLE PROVIDED FOR THE TEAM
Indicators
Task Type
Name
Duration
Start Date
Finish Date
Predecessors
Resources
Text1 (Branch Office)
Text2 (Project Name)
Text3 (Case Type)

## Slide 18: Solution Example
Case Backlog Clearing
  Running record of backlog projects performed for each Branch Office
  Analysis of case types
  Analysis of backlog recurrence
Projects
Tasks
Assignments
Resources
Branch Offices

## Slide 19: Solution Limitations
No Microsoft Project Server
Data would not be imported into Microsoft Access
  It would have found its way back into Excel anyway
  No one on the team knows Microsoft Access
Existing Microsoft Project export options did not satisfy a simple process the team could perform
  Export mapping
  Visual reports
A shared template was easier to update and make accessible to the team than updating everyone’s Global.mpt
VBA (Visual Basic for Applications) wouldn’t be used in either Project or Excel

## Slide 20: Importing Process
Custom table in Microsoft Project containing the same fields in a matching Excel Table
Projects
Excel Table with Specific Fields
Branch Offices
MICROSOFT EXCEL
MICROSOFT PROJECT
Tasks
Project A
Tasks
Project B
Tasks
Project C
Tasks
Project D
Tasks
Project E
Tasks
Project F
Custom Table
Matching Excel Fields
Custom Table
Matching Excel Fields
Custom Table
Matching Excel Fields
Custom Table
Matching Excel Fields
Custom Table
Matching Excel Fields
Custom Table
Matching Excel Fields

## Slide 21: The Selected Solution
Customized Microsoft Project Template
  Used to plan and track projects
  Contains necessary reports for branch managers and directors on immediate project plan and status
  Contains an easy export option after the project was completed
Microsoft Excel Data Collection
  Contains all completed project tasks
  Contains summary reports
    By branch office
    By case types

## Slide 22: Adapting Microsoft Project

## Slide 23: Fields for Analysis
Branch Office
Project Name
Case Type
Name (Task Name)
  “Earlier Months”
  “Previous Month”
  “Current Month”
Case Month
Total Cases
Processing Hours
Group By Fields
Data to Aggregate

## Slide 24: Creating Custom Fields
Text Fields
  Branch Office
  Project Name
  Case Type
Number Fields
  Total Cases
  Remaining Cases
  Cases Per Hour Est
  Cases Processed (Calculated)
  Estimated Remaining Hours (Calculated)
Date Field
  Case Month

## Slide 25: Creating Lookups
Enables Consistent Data Entry
  Sorting
  Filtering
  PivotTables

## Slide 26: Calculated Fields
Cases Processed
  Total Cases minus Remaining Cases
  Manual input of Remaining
Est Remaining Hours
  Remaining Cases divided by Cases Per Hour
  Could not use VBA to update Project field Remaining Hours

## Slide 27: Customizing Tables
Select the pre-existing table with the fields you want to start with
Right-click column headings and insert the new columns you want
Right-click and remove the columns you don’t want
On the View Tab, select Tables and Save the Fields as a New Table
Select Reset to Default to reset the original table

## Slide 28: Date Formatting Options
The abbreviated name of the day of the week will translate into Excel as Text
Changing the Date Format to the short date format ensures Excel will read the pasted dates as dates

## Slide 29: Shared Templates

## Slide 30: The Custom Table

## Slide 31: The Custom Table

## Slide 32: Microsoft Excel Tables

## Slide 33: Essential Excel Concepts
Excel is not a relational database
  It can use formulas to reference unique identifiers in a related data collections
  There is no enforced integrity
    The table could be referencing an identifier that doesn’t exist
    Data Validation is limited
    There is no “true” enforcement of unique identifiers
The user must follow specific design methods for Excel to recognize that what they’ve created is a table

## Slide 34: Cell References
Cell references in formulas should be used when the data being referenced will most likely remain unchanged
If the range expands, the user must update the function to include new cells

## Slide 35: Named Ranges
If the same set of numbers is referenced several times, a proxy name can be created and used instead of the cells
If the list expands, the user can update the reference in the Name Manager and update all references to it

## Slide 36: Data Tables
Added in version 2007
As the table expands, references to the table will recognize the new data
Formulas and PivotTables will not need to have their references updated

## Slide 37: Needs for Proper Excel Tables
Begin the data table in cell A1
  Data presentations created by PivotTables and PivotCharts are more print-worthy
Each column must have a column heading
Use a single row for column headings
Each column should contain data of one type only
  Text
  Dates (either it’s a date or it’s blank)
  Numbers
Do not skip rows or columns within the list

## Slide 38: Somewhat Simple Copy and Paste
With the exception of having to delete the column headings each time, the process is simple
Because the destination of the paste is defined as a table, all of the PivotTable reports only needed to be refreshed
Running a custom export map, opening the exported file, and pasting it into the Excel table was too many steps

## Slide 39: Data Type Issues
Work and Duration Labels prevent any calculations

## Slide 40: Excel Functions
=SUBSTITUTE(text to revise, text to replace, replacement text)
=SUBSTITUTE(“82 hrs”, “ hrs”, “”)
=VALUE(SUBSTITUTE(L2,"hrs",""))
=VALUE(text that should and can be a number knowing this doesn’t remove letters and other stuff that’s preventing it from being one)
=VALUE(“82”)

## Slide 41: Best Strategies with Functions
Columns Pasting New Data Into
Functions that fill automatically in data tables

## Slide 42: Excel PivotTables
DATA SOURCE
PivotTable 1
PivotTable 2
PivotTable 3
PivotTable 4

## Slide 43: PivotTable Fields
FILTERS
Isolates data (i.e. a report on just 2018 projects, all projects performed for one branch)
ROWS
Groups together (consolidates to one row) all the same items from the data column placed here
COLUMNS
Groups together (consolidates to one row) all the same items from the data column placed here
VALUES
Automatically COUNTs text fields and SUMs number fields by whatever is placed in ROWS and COLUMNS

## Slide 44: Case Type by Month

## Slide 45: Case Type by Month

## Slide 46: Additional Example Data

## Slide 47: Conclusion
Concentrated only on tasks
  Prorated timescale of data possible, but not “simple”
  Exporting Usage Views (Assignment Data) is far more complex
Shaped perfectly for this example
  Task naming conventions
  Calculations of items or units produced
Excludes other technologies
  Access to technologies may alter the process

## Slide 48: Questions?

## Slide 49
Data Analysis using Project with Excel
November 28, 2018x @ 12pm-1pm EST jbongiovani@edwps.com
Thank You!
Notes: Start Recording
We are going to go ahead and get started with todays session on xxxxx.