## Slide 1
Analogous & Parametric Estimating Schedule Template
April 15, 2020 @ 12pm-1pm EST Oliver Gildersleeve Jr., PMP, MCTS
ogilders@sbcglobal.net
USA 650-328-6087
Notes: Start Recording
We are going to go ahead and get started with todays session on xxxxx.

## Slide 2: What you will see: Approach, then Views
3 custom views (View = Table, Filter, Group)
  “04 – Estimating template initial data” (In template)
    Use a past project or published data
  “05 – Estimating the specific project” (In project schedule)
    Include estimating uncertainty
  “06 – Estimating data improvement”
Adding: Risk Reserve & Estimating Uncertainty Buffer
Tracking task progress correctly
Transferring custom artifacts to your schedules

## Slide 3: Approach - Best Way: Estimating Two Ways
Parametric - Tasks: Count * Unit effort
Analogous - Summaries: Effort * multiplier
What’s the trouble: (Harvard Business Review)
  Looking ahead, not back. Over-confidence. Ignoring competition. Durations.
  https://hbr.org/2003/07/delusions-of-success-how-optimism-undermines-executives-decisions
What’s the cure:
  Develop & reconcile “Top Down” & “Bottom Up” estimates
  https://hbr.org/2020/02/use-data-to-revolutionize-project-planning?utm_campaign=hbr&utm_source=twitter&utm_medium=social
What executives want to know - quickly:
  How soon? How much? Who’s needed?
Top Down
Bottom Up

## Slide 4
Task scaling.
Top Down
Parametric Estimating – Example

## Slide 5
Summary task scaling. Negotiate: Delivery, Cost, Resources.
Top Down
Analogous Estimating – Example

## Slide 6
Example: 20 hour task. Doing 4 hours/workday.
  1 isolated task, takes 1 work-week
  2 concurrent tasks, takes 2 work-weeks for each task
  3 concurrent tasks, takes 3 work-weeks for each task
So, Work is stable, improvable
Durations unstable, unimprovable
Beginners: Durations. Intermediates: Work
Estimating Durations - What’s wrong ?

## Slide 7: Precision: Work Definition Refined
Level of Effort: Time not on a particular task
  E.g. Meetings, status reports, etc.
Net Work is timesheet hours producing task objects
Gross Work (Net work + Level of Effort)
  Gross work sums to a standard day, e.g. 8 hours/workday
For scheduling tasks, seek median Net Work
  Add a project Risk Reserve & Estimating Uncertainty Buffer
For Labor Cost, seek Gross Work
  Labor rate * Gross work
  Labor rate * (Net work + Level of Effort)

## Slide 8: So, how do you get started ?
Set up a schedule template (.mpt) from a medium size, past project
Allocate the past project Duration to Summary task Durations
Allocate Summary Durations to their Task Durations
Usual waiting: use lags on successors, e.g. 24FS+4
  Awaiting contracts, approvals, resource availability, materials, etc.
  Unusual waiting: insert a task.
  To finish, Inactivate unusual waiting

## Slide 9: Past Project Interviews, each task
Interview past project resources or you find published data
  Say you want to exclude meetings, interviews, status reporting, supervision, other
  Exclude risks that happened because risk will be covered by a Risk Reserve
On how many days during the duration was work performed?
How many persons worked producing each task’s output?
Average net workhours/workday on tasks?
5. Ask, what is the primary parameter or factor for scaling?
6. How many items of each factor were there?
  E.g. Needs, Modules, Customers, Pages
  Fewer factors: faster, but less precise the estimating
  7. Ask what is the likelihood the estimate is sufficient?
    Get 80% and 50% sufficient estimates.

## Slide 10
Copy template to make a future project schedule (.mpp)
Scale the tasks future project size
  Use ratios to make conservative estimates. Check consistency.
  Just before product delivery task
    set Deadline to get Total Slack to show the critical path
Add Shock Absorbers after the deadlined task
  Add a project Risk Reserve
  If using median estimates, add an Estimating Uncertainty Buffer
Forecast the future project

## Slide 11
Execute the project using median estimates
Update each task with
  Actual Start, Actual Work, and Remaining Work
  If Peak units differ from Assignment Units, discuss adjustments
After the 1st task using each parameter, if needed:
  Adjust the “N14 Items in Project” for its remaining tasks
After 1st task by each resource, discuss their Assignment Units
If Buffer penetrated 1/3, plan recovery
If Buffer penetrated 2/3rds, recover Buffer then needed
Update Correctly

## Slide 12
If a common case, in “06 Estimating data improvement” enter in the “F17 Use” column “Yes”
  Increment “Yes: Observations +1” (similar to averaging)
  Copy “T20 New Work Number”
In template’s “04 Initial Data in Template”
  Paste in the “T21 Work Number”
Updating and estimating cycle: CLOSED LOOP
Improve Estimating Data

## Slide 13
Problem: Actual Work updates planned Work
  But, to improve Work estimating data
    Need to retain the original Work estimate
  Solution: Copy/paste Work into a Text column
    “T21 Work Number”
Problem: Work data ends in “… hrs”
  But, to improve estimating data, need to do calculations
  Solution: Format; Find; Replace “ hrs” with “” (nothing)
Tricks necessary in Microsoft Project

## Slide 14
In specific schedule, “Gantt Chart 2”,
  In View; Outline: Level 1 (or 2 if using Project Summary Task)
  Copy columns: Task Name, Work, Duration
  Paste columns below the parametric schedule or in a blank schedule
    Above these tasks, insert Summary, “Analogous Plan”
In Analogous Plan, change all tasks to Fixed Work
  One task at a time, copy Duration
    Enter “Resource”. If Duration changes, replace Duration.
      Copy Peak units. Delete Assignment Units. Paste into Assignment Units.
  Change all tasks back to Fixed Units, Effort Driven: No
Make an Analogous Schedule – 1 of 2

## Slide 15
Link tasks with Predecessors to match Parametric Plan Finish dates
  Add Risk Reserve and Estimating Uncertainty Buffer using lags.
In view, “04 Template Initial Data”
  Copy column, Work, & paste to , “ T21 Work Number”
    Task; Find (dropdown); Replace: “ hrs” to nothing in T21 column
  In column, “ N16 Items in Template”, enter “1” & drag down
In view, “05 Estimating the Specific Project”
  In column, “N14 Items in Project”, enter “1” & drag down
Set Baseline: Format; Baseline, click Baseline; OK
Make an Analogous Schedule – 2 of 2

## Slide 16
How do I Scale the Analogous Schedule?
  In “05 Estimating the Specific Project”
    Optionally, in “T15 Factor”, enter “Analogous”
    In “14N Items in Project” enter a scaling multiplier, e.g. 1.25
    Copy “N3 Median Work” column into “Work” column
    Negotiate: Adjust scaling multipliers
      Delivery date, Cost and Resources

## Slide 17: Scale Data Parametrically: ways 1 & 2
Factors: Fixed, Pages, Analogous, Parametric
Fixed: If a task’s Work is same in all sizes of these projects
  In “04…(template)”, enter 1. In “05…(project)”, enter 1.
  Project: Work = Template: Median Scaled Work
2. Pages: If the deliverable is a document
  Enter the number of equivalent new pages if revising the deliverable
    Adjust work until workhours per page is appropriate, e.g. 90 minutes
      If estimating work to produce a first draft, maybe 30 to 45 minutes

## Slide 18
3. Analogous: If the task does not produce items
  Enter “1” in “04…(template)”
  Enter subjective scaling multiplier in “05…(project), e.g. 1.25
  Project Work = Template Work * scaling multiplier
Parametric: If the task involves items
(e.g. Needs, modules, sessions)
  In “04…(template)” enter Items in template
  In “05…(project)” in Items in Project
  All tasks scaled by the same Factor have the same number of items
    (Except pages)
  Project Work = Template unit Work * Items in Project
  First task using a Factor may adjust the items count
Scale Data Parametrically: ways 3 & 4

## Slide 19: Are there other considerations?
Adjust estimates for: (The CMMI-1.3, pg.~284.)
  Skill levels of managers
  Staff knowledge and training
  Facilities for engineering and manufacturing
  Computer & tool capabilities
  Project approach and methods
  Security considerations, Etc.
Creative tasks - Decompose tasks into:
  Discovery - Like Search & Rescue pattern
    Median: 50% of pattern. Conservative: 80% of pattern
  Implementation

## Slide 20: Copy views to your templates?
  Use File > Organizer
    From right to left: Groups, Fields, Calendars, Filters, Tables, Views
      (If left to right, column names & formulae are lost)

## Slide 21: Summary of Approach
Make a schedule template with unit effort data
Get template data from a past project of medium size
  Factor out: risks, issues, unusual waiting, change requests
  Factor in: lessons learned, improvements in processes & tools
Make a specific project schedule
  Scale by equivalent new pages, items in the project, or multipliers
    Adjust for other considerations: knowledge, complexity, productivity, etc.
  Use ratios to make conservative estimates
    Or work backwards: Use ratios to derive median estimates
Execute projects using median estimates

## Slide 22
Give up fallacies
  On-time tasks produce on an time project
    Wrong: Late starts and surprises produce
      Rushing, short cutting, increased error rates, late delivery
  Estimate Work. Calculate Durations: = Work / Assignment Units
Update – (not by %-complete)
  Update by Actual Start, Actual & Remaining Work
  Show all progress in the past
  Move any incomplete work to the future
  Upon initial factor and resource updates
    Adjust resource’s Assignment Units and task’s “Items in Project”
  Use buffer penetration to trigger schedule recoveries
Gather & improve template estimating data
Conclusions:
Connect Estimating & Tracking

## Slide 23
Estimating views: Analogous & Parametric
  Using data from past, medium size project or commercial sources
  Scaling of estimating data for a specific project
  Improving estimating data continuously
Adding a Risk Reserve & Estimating Uncertainty Buffer
Warning: Get ready for BRPs
  (Bonuses, Raises, Promotions)
What did you see?

## Slide 24
Analogous & Parametric Estimating Schedule Template
April 15, 2020 @ 12pm-1pm EST Oliver Gildersleeve Jr, PMP, MCTS
Consultant, Instructor, Mentor
ogilders@sbcglobal.net
USA 650-328-6087
Thank You!
Notes: Start Recording
We are going to go ahead and get started with todays session on xxxxx.

## Slide 25: Analogous & Parametric Estimating Schedule Template
Closing the loop between tracking & estimating
Oliver Gildersleeve, PMP, MCTS
Consultant, Instructor, Mentor
ogilders@sbcglobal.net
USA: 650-328-6087
25

## Slide 27
Subjective estimates based on human recall
  Appropriate where there is no history
  Where history is corrupted, inaccurate, different
Modeled estimates based on historic data
  Much better where tasks are process steps
    As in project schedule templates
  Where Actual Work is recorded daily, reported weekly
    Stable, scalable, adjusted for complexity and productivity
Which Estimates are Better ?

## Slide 28: Don’t Estimate Conservative Durations
Why are used widely?
  Gantt Chart view: Duration column appears, not Work
Why are estimates conservative?
  Management criticizes late tasks
  Single-point estimates: inappropriate for creative tasks
    There’s no place for range estimates (high, median, low)
  Lack of project priorities motivates multi-tasking
    Degrades productivity, obscures actual work effort
Interrupted tasks aren’t split; Durations are extended
Firm Fixed Price Contracts motivate hiding Work

## Slide 29
Critical tasks start on their planned Start date
  Apply assigned workhours/day
  Finish without delay: defend and expand Total Slack
Interrupt non-critical tasks
Select next task based on enterprise project priority
Alert Project Manager as soon as doubt arises
Keep the successor resource aware of your progress
  Don’t wait for a status meeting
At Kick-off, require

## Slide 30: What’s the Better Way ?
Plan from a project schedule template, estimate Work
  Template: tasks are process steps
  All projects that use the process can use the template
  Common project structure and vocabulary
  Resources: daily record Actual Work
    Track critical tasks daily (Scrums)
    Weekly report Actual and Remaining Work
Collect Actual Work & improve estimating data:
  Reverse scaling back to the template’s size & adjust its data
  If 1/3rd of Buffer penetrated, plan recovery
  If 2/3rds of Buffer penetrated, implement recovery plan

## Slide 31
One-off schedules with conservative durations
    Allowing for risks, issues, complexity, and productivity
Consequences:
  Resources do other work until remaining time is minimal
  Then, surprises on critical tasks
    Make the product/service late
    Cause heroic efforts to finish critical tasks on time
    Cut into adequate testing
    Executives cut “padding,” resources estimate more conservatively
Project Management Traditions

## Slide 32
Construction
  John S. Page Estimating Manuals
  RS Means Yearly Cost Data Books
  Compass International Yearly Cost Data Books
  Design Cost Data Magazine
  The Chief Estimator Software
  Engineering News – Record
  AACE
Other
  IFPUG Functional Size Measurement
  Industrial Piping & Equipment Manual
  Cost Engineering (CESK)
  Book time for warrantees
Your own data is best
External Sources of Data

## Slide 33
04 Estimating the Template initially
  Work = 12 hrs
  Work Number = 12 Becomes 14
  Items in Template = 4
  Work per Item = 12 / 4 = 3
05 Estimating the Specific Project
  Items in Project = 5
  Work in Project = 3 * 5 = 15
06 Estimating data improvement
  Actual Work = 20, increment “Yes: Observations+1
  New Work Number = 12 + (20 * 4 / 5 – 12) / 2 = 14
Example

## Slide 34
Add an aggregate Risk Reserve
  DProduct of likely (delays * likelihoods after mitigation)
    Or the largest delay from any of the risks
  Include a lag on last development task’s successor
    e.g. Task: “77 Product market ready”. Successor: 78FS+3wk.
      Manually adjust as risk delays happen
    For risks that may recur, rebuild the Risk Reserve when used
What About Risks?

## Slide 35
Enter Estimating Uncertainty Ratios = High / Median estimates
  E.g. 15 hours / 10 hours = 1.5
Median estimate: Actual Work < estimate 50% chance
  Allows for a reasonable level of minor issues
  Allows for higher complexity, lower productivity
  Keeps ratios consistent through out the schedule
  Range should fix when parameter first used
Copy High estimates into Work. Get delivery date.
Copy Median estimate to Work. Get delivery date.
Estimating Uncertainty Buffer = 1/2 delivery date difference
  Depends on tolerance for product lateness
What About Uncertainty?